## Inc Matrix
Use Case | Use Case Name | Iteration 2* (10/29/20) | Iteration 3* (11/03/20) | EUC | SD
UC 1 | Register | 1(SD)
UC 2 | Login | 1
UC 3 | Logout | 1
UC 4 | View Profile | 1
UC 5 | Update Profile | 1
UC 6 | Search Vehicles | 1
UC 7 | Select Vehicle | 1
UC 8 | Reserve Rental | 1(SD)
UC 9 | View Rental History |  | 1 | Done | SD
UC 10 | View Reservation Summary |  | 1 | Done
UC 11 | Update Rental Details |  | 1 | Done
UC 12 | Cancel Rental Reservation |  | 1 | Done
UC 13 | Search All Users | 1
UC 14 | View User | 1
UC 15 | Modify User Profile | 1
UC 16 | View Reservation Calendar |  | 1 | Done
UC 17 | View Rental Details |  | 1 | Done
UC 18 | Delete Reservation |  | 1 | Done
UC 19 | View Available Cars | 1
UC 20 | Search for Cars | 1
UC 21 | View Selected Car | 1