## Inc Matrix
Use Case | Use Case Name | Function path | Iteration 2* (10/29/2020) | Assigned to | Iteration 3* |  | EUC | UIP
UC 1 | Register |  | 1 | Omkar |  |  | Done
UC 2 | Login |  | 1 | Omkar |  | Completed | Done
UC 3 | Logout |  | 1 | Omkar |  | InProgress | Done
UC 4 | View Profile |  | 1 | Omkar |  | Not Started | Done
UC 5 | Update Profile |  | 1 | Omkar |  |  | Done
UC 6 | Search Vehicles | Search Vehicles ---> Select Vehicle --> Reserve Rental | Completed | Gaurav |  |  | Done
UC 7 | Select Vehicle |  | Completed | Gaurav |  |  | Done
UC 8 | Reserve Rental |  | InProgress | Gaurav |  |  | Double Check
UC 9 | View Rental History | View Rental History --> View Reservation Summary --> {Update Rental Details, Cancel Rental Reservation} |  |  | 1
UC 10 | View Reservation Summary |  |  |  | 1
UC 11 | Update Rental Details |  |  |  | 1
UC 12 | Cancel Rental Reservation |  |  |  | 1
UC 13 | Search All Users | Search All Users ---> View User --> { Modify User Profile } | Not Started | Neel |  |  | Done
UC 14 | View User |  | Not Started | Neel |  |  | Done
UC 15 | Modify User Profile |  | Not Started | Neel |  |  | Done
UC 16 | View Reservation Calendar | View Reservation Calendar --> View Rental Details --> Delete Reservation |  |  | 1
UC 17 | View Rental Details |  |  |  | 1
UC 18 | Delete Reservation |  |  |  | 1
UC 19 | View Available Cars | View Available Cars, Search for Car --> View Selected Car | Not Started | Jeevesh |  |  | Done
UC 20 | Search for Car |  | Not Started | Jeevesh |  |  | Done
UC 21 | View Selected Car |  | Not Started | Jeevesh |  |  | Double Check